## Firefox Project - Work Schedule
[6 empty] | June | [18 empty] | July
| 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Preliminary Tasks
Receive Assignment | Team
Team Meeting | Team
Establish File Repository | Rod
Create Document Templates | Rod
Build Project Plan
Create Work Schedule | Rod
Contribute to Project Plan Document |  | Team
Submit Project Plan & Work Schedule |  |  |  |  | Team
Build Virtual Machines
Establish VM Baseline Configuration | [5 empty] | Team
Build VMs | [7 empty] | Team
Research
Research Fuzzers - Sully, Peach, Codenomicon | [10 empty] | Jon Mark
Research Browser Privacy - Firefox vs. Opera | [10 empty] | Seth
Research Firefox Enterprise Deployment | [10 empty] | Rod
Research Firefox Policy Management | [15 empty] | Rod
Testing
Sully Fuzzing | [13 empty] | Jon Mark
Peach Fuzzing | [15 empty] | Jon Mark
Codenomicon Fuzzing | [17 empty] | Jon Mark
Firefox Outbound Connections | [13 empty] | Seth
Opera Outbound Connections | [16 empty] | Seth
Document Findings
Fuzzing Summary | [19 empty] | Jon Mark
Privacy Summary | [19 empty] | Seth
Enterprise Management Summary | [19 empty] | Rod
Establish Conclusion | [23 empty] | Team
Create CIO Presentation of Findings | [24 empty] | Team
Final Paper
Editing, Polishing, Proofreading | [25 empty] | Team
Submit Final Paper | [30 empty] | Team
Project Plan Due