## Firefox Project - Work Schedule
[6 empty] | June | [18 empty] | July
| 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Preliminary Tasks
Receive Assignment | Team | ✔
Team Meeting | Team | ✔
Establish File Repository | Rod |  | ✔
Create Document Templates | Rod |  | ✔
Build Project Plan
Create Work Schedule | Rod |  | ✔
Contribute to Project Plan Document |  | Team |  |  | ✔
Submit Project Plan & Work Schedule |  |  |  |  | Team | ✔
Build Virtual Machines
Establish VM Baseline Configuration | [10 empty] | Team |  | ✔
Build VMs | [10 empty] | Team |  | ✔
Research
Research Fuzzers - Sully, Peach, Codenomicon | [12 empty] | Jon Mark | [8 empty] | ✔
Research Browser Privacy - Firefox vs. Opera | [12 empty] | Seth | [8 empty] | ✔
Research Firefox Enterprise Deployment | [12 empty] | Rod | [6 empty] | ✔
Research Firefox Policy Management | [19 empty] | Rod |  | ✔
Testing
Sully Fuzzing | [21 empty] | Jon Mark |  | ✔
Peach Fuzzing | [23 empty] | Jon Mark |  | ✔
Codenomicon Fuzzing | [25 empty] | Jon Mark |  | ✔
Firefox Outbound Connections | [24 empty] | Seth |  |  |  |  | ✔
Opera Outbound Connections | [24 empty] | Seth |  |  |  |  | ✔
Document Findings
Fuzzing Summary | [24 empty] | Jon Mark
Privacy Summary | [24 empty] | Seth
Enterprise Management Summary | [24 empty] | Rod
Establish Conclusion | [32 empty] | Team
Create CIO Presentation of Findings | [34 empty] | Rod
Final Paper
Editing, Polishing, Proofreading | [34 empty] | Team
Submit Final Paper | [37 empty] | Team
Project Plan Due